## Sheet1
|  |  | August | [20 empty] | September | [12 empty] | October
| Who | 1 | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Break | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12
|  |  | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 |  | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30
Introduce business context and data | OJ
Open data portal and PowerBI trail | YZ
Statement of Work | YZ
Introduce dashboard template | OJ
Data sets publish | OJ
Seasonality analysis | YZ
Dashboard 1 | YZ
User-test 1
Weekly catch-up | YZ&OJ | bar: Week 7 22; Week 8 29; Week 9 6
Mid-term review
Dashboard 2 | YZ | bar: Week 7 21 to Week 8 2
Anomalies detection | YZ | bar: Week 8 28 to Week 8 2
User-test 2 | bar: Week 8 28 to Week 8 2
Documentation | YZ | bar: Week 8 28 to Week 9 9
Poster & Show Case | YZ | bar: Week 9 5 to Week 10 16
Stakeholder review | NU | bar: Week 11 19 to Week 11 23
Additional Presentation to Business Stakeholders | YZ | bar: Week 11 19 to Week 11 23
Work Portfolio | YZ | bar: Week 11 19 to Week 12 30